## to-do
order | activity | prev activity | description | responsible | involved | status | optimistic (days) | moderate (days) | pessimistic (days) | expected (days) | delivery date | milestone (link) | comments
1 | 0 | NA | signature of Knotion-OECD agreement | OECD | Knotion | complete | 0 | 0 | 0 | 0 | 2018-01-25 | https://drive.google.com/open?id=0B4B3BxoxX7LTVVdYX1Y1SmpnVXN0a3MzUW5pcmo0TzZ6elFJ
2 | 1 | 0 | establish procedures for the security, protection, and confidentiality | Knotion | Knotion RD | complete | 0 | 0 | 0 | 0 | 2018-01-25 | https://drive.google.com/open?id=1JjlY1XEt_QOaKsG-I57pNnZ-O2JV4UId
3 | 2 | 0 | translate and adapt all materials | Knotion | Knotion RD | complete | 0 | 0 | 0 | 0 | 2018-01-25 | https://drive.google.com/open?id=0B4B3BxoxX7LTY2Y2Rlo4Z1NNLVE
4 | 9 | 8 | compile a database of schools to be tested | Knotion | Knotion RD | complete | 0 | 0 | 0 | 0 | 2018-01-25 | https://docs.google.com/spreadsheets/d/1hvJH3RLpYeawWU3J7z20wxYwKSQpMrgPHw3c7-r12gY/edit?usp=sharing
5 | 14 | 9 | train test makers and coders | Knotion | 2e | pending | 1 | 2 | 3 | 2 | 2018-01-27
6 | 10 | 9 | create sampling procedures for students | Knotion | 2e | pending | 3 | 5 | 7 | 5 | 2018-01-30
7 | 11 | 10 | identify school coordinators | Knotion | Knotion RD | pending | 3 | 5 | 7 | 5 | 2018-02-04
8 | 12 | 9 | recruit tests administrators | Knotion | Knotion RD | pending | 7 | 15 | 30 | 18 | 2018-02-12
9 | 13 | 12 | train test administrators | Knotion | 2e | pending | 1 | 2 | 3 | 2 | 2018-02-14
10 | 3 | 2 | verify translated and adapted versions of materials | OECD | Capstan | in progress | 15 | 21 | 30 | 22 | 2018-02-16 |  | Pending comments from PfS team
11 | 6 | 0 | develop school level reporting templates | OECD | OECD | in progress | 15 | 30 | 50 | 32 | 2018-02-26 |  | Pending comments from PfS team
13 | 4 | 2 | asset illustration and digitization | Knotion | Knotion Art | in progress | 50 | 64 | 76 | 64 | 2018-03-30 | https://drive.google.com/open?id=1VeVzIOrYCxtdFn4kCA9SpzheOWPze8Su
12 | 8 | 3 | recruit non-Knotion schools | Knotion | Knotion RD | in progress | 30 | 50 | 70 | 50 | 2018-04-07 | https://goo.gl/forms/9MyYY2UkhJo3WeXY2
14 | 5 | 3 | develop web-based testing system | Knotion | Knotion IT | in progress | 50 | 60 | 70 | 60 | 2018-04-17
15 | 15 | 5 | administer the test | Knotion | Knotion Op | pending | 15 | 21 | 30 | 22 | 2018-05-09
16 | 16 | 15 | score and mark test responses | Knotion | Knotion IT | pending | 15 | 21 | 30 | 22 | 2018-05-31
17 | 17 | 16 | conduct data entry for test and questionnaire responses | Knotion | Knotion Op | pending | 10 | 15 | 20 | 15 | 2018-06-15
18 | 18 | 17 | conduct cognitive item validation study | Knotion | 2e | pending | 30 | 50 | 60 | 47 | 2018-08-01
19 | 19 | 18 | calculate school level results | Knotion | 2e | pending | 30 | 50 | 60 | 47 | 2018-09-17
20 | 21 | 19 | calculate knotion level reports | Knotion | 2e | pending | 15 | 30 | 30 | 25 | 2018-10-12
21 | 20 | 19 | produce school level reports | Knotion | 2e | pending | 30 | 50 | 60 | 47 | 2018-11-03
22 | 22 | 21 | produce knotion level reports | Knotion | 2e | pending | 30 | 50 | 60 | 47 | 2018-11-28
23 | 7 | 0 | provide technical oversight | OECD | OECD | in progress | 0 | 0 | 0 | 0 | 2018-11-28 |  | Pending comments from PfS team
Formulas:
delivery date = IF([expected (days)] = 0, L2 + 0, INDEX(L:L, MATCH([prev activity], B:B, 0), 1) + [expected (days)])

## source
Task | Responsible | Status
Provide test materials | OECD | Done
Lead translation and adaptation workshop | OECD | Done
Identify contractors for Knotion | OECD/Knotion | Done
Establish procedures for the security, protection, and confidentiality of all materials | Knotion | Done
Contact external contractor | Knotion | In progress
Translate and adapt all testing materials | Knotion | Done
Verify translated and adapted versions of test materials | OECD | Pending
Develop school level reporting templates | OECD | Pending
Compile a database of schools to be tested | Knotion | Done
Create student samples | Contractor/Knotion | In progress
Recruit test administrators | Contractor | Pending
Recruit test markers and coders | Contractor | Pending
Train test administrators | Contractor | Pending
Train test markers and coders | Contractor | Pending
Identify school coordinators | Knotion | In progress
Develop an iPad version of the tests | Knotion | In progress
Administer the test | Contractor | Pending
Score and mark test responses | Contractor | Pending
Conduct data entry for test and questionnaire responses | Contrator | Pending
Perform pilot / mode effect study | Contractor | Pending
Perform cognitive item validation study | Contractor | Pending
Calculate school level results | Contractor/Knotion | Pending
Produce school level reports | Contractor | Pending